## WBS
Work Breakdown Structure - Phase 1: Excel Property Management Web Ledger
Note: This project follows a hybrid Agile-Waterfall approach, with three four-week iterations (Alpha. Beta, Production) for phase 1 of the Excel Property Management Web Ledger.
WBS ID | Task/Subtask | Description (Summary) | Assigned Role | Estimated Duration
1 | Project Management & Planning | Oversee planning, scheduling, cost estimation, communication with EPM stakeholders. | Project Manager | 2 weeks
1.1 | Define Scope & Objectives | Review charter, confirm features, define Phase 1 deliverables & roles. | Project Manager | 3 days
1.2 | Schedule & Resource Planning | Develop timeline, assign resources, set milestones for Alpha/Beta/Prod. | Project Manager | 3 days
1.3 | Risk Management & Budget Approval | Identify risks, prepare mitigation plan, review cost assumptions with management. | Project Manager | 4 days
2 | System Architecture & Design | Establish technical architecture for the web solution and define system interfaces. | Backend Engineer / DB Developer | 2 weeks
2.1 | Requirements Analysis & Use Cases | Translate business rules into techincal requirements for auth, roles and ledger entries, roles, and activity logs. | All engineers + PM | 1 week
2.2 | Database Schema Design | Design tables for properties, tenants, ledger entries, roles and activity logs. | Database Developer | 1 week
2.3 | System Architecture Diagram & APIs | Define frontend-backend interfaces and data dlow architecture | Backend Engineer / PM | 4 days
3 | Frontend Development (Web Interface) | Develop secure, role-based browser UI accessible across devices | Frontend Engineer | 3 weeks
3.1 | Authentication & Role-Based Login UI | Build login oage with admin/manager/analyst views. | Frontend Engineer | 1 week
3.2 | Ledger Entry Dashboard | Create forms for rent charges, credits, and property comments. | Frontend Engineer | 1 week
3.3 | Reporting & Analytics UI | Build charts/tables for financial and property reports. | Frontend Engineer / Analyst | 1 week
3.4 | Responsive Design & UX Polish | Optimize layout for mobile and tablet devices. | Frontend Engineer | 3 days
4 | Backend Development & Integration | Implement server logic, security, logging, and database connection layer. | Backend Engineer | 3 weeks
4.1 | API Implementation | Develop REST endpoints for ledger entries, authentication, and reports. | Backend Engineer | 1.5 weeks
4.2 | Security & Access Control | Implement password hashing, JWT/session tokens, and role-based authorization. | Backend Engineer | 1 week
4.3 | Activity Logging & Audit Trail | Log logins and critical actions for auditing. | Backend Engineer | 3 days
4.4 | Database Integration & Backup Setup | Connect to Access/SQL DB, enable automated backups. | Database Developer | 4 days
5 | Testing & Quality Assurance | Validate functionality, usability, and security before releases. | QA Engineer | 2 weeks
5.1 | Unit & Integration Testing | Test API endpoints and UI modules for correct behavior. | QA Engineer | 1 week
5.2 | User Acceptance Testing (UAT) | Gather feedback from Sparky and staff on beta build. | QA Engineer + PM | 4 days
5.3 | Security & Performance Testing | Perform role-based penetration and load tests. | QA Engineer | 3 days
6 | Deployment & Maintenance | Prepare production server, release builds, and post-launch support. | Backend Engineer / PM | 2 weeks
6.1 | Alpha / Beta / Release Deployment | Host on test server for internal validation. | Backend Engineer | 1 week
6.2 | Final Production Deployment | Move stable build to secure host with database migration. | Backend Engineer | 4 days
6.3 | Maintenance & Documentation | Deliver user manual, admin guide, and handover docs. | PM + All Engineers | 4 days

## WBS Dictionary
WBS Dictionary (Task Details)
WBS ID | Task Name | Purpose & Deliverables
1 | Project Management & Planning | Define scope, timeline, and resource allocation; conduct risk analysis and approve schedule with EPM stakeholders.
2 | System Architecture & Design | Translate requiements into technical architecture with ER diagram, data flow, and API contracts.
3 | Frontend Development | Build role-based broswer UI with dashboards for Admin, Manager, and Analyst roles following UX best practices.
4 | Backend Development & Integration | Implement secure REST services, data persistence, authentication, and logging.
5 | Testing & Quality Assurance | Ensure functional correctness and security compliance through unit and UAT testing.
6 | Deployment & Maintenance | Deliver Alpha, Beta, and Production builds, host application, and provide post-launch support and documentation.

## Iterative Plan
Iterative Delivery Plan (Three Releases)
Release | Focus / Goals | Key Features Delivered
Alpha Release | Core prototype and architecture validation | - Basic login/authentication system - Database schema created and connected - Admin dashboard for property overview - UI wireframe for ledger entry
Beta Release | Funtional system for user testing | - Role-based access control (Admin, Manager, Analyst) - Ledger entry form with validation - Reporting and data summary features - Activity logging and audit trail - User acceptance testing feedback loop
Production Release | Final stable system with security and polish | - Complete frontend styling and responsive UI - Full CRUD ledger operations - Database backup and restore scripts - Performance & security tests - Documentation and training delivery